## Sheet1
Workflow Description | Workflow Type | Sub Workflow Type | Subworkflow Task | Construction Workflow |  | CheckList | Notes section to put orders in?? |  | Task List
Make an offer | Main Workflow | Main Workflow | N/A | DEMO |  |  |  |  | Someone can add to their own task list
Close On property | Main Workflow | Main Workflow | N/A | All items removed |  | Initial order ordered |  |  | Chase/Kevin can add a task to anyones task list
Put keys in lockbox | Main Workflow | Main Workflow | N/A | all flooring out |  | Tile ordered
Get utilities Turned on | Main Workflow | Main Workflow | N/A | bathrooms demo |  | Flooring ordered
Verify all utilities are on and not locked | Main Workflow | Main Workflow | N/A | Cabinets out |  | Paint ordered
Initial Walk through | Main Workflow | Main Workflow | N/A | Walls taken out? | yes/no | Amazon ordered
Contractor walk through | Main Workflow | Main Workflow | N/A |  |  | Fireplace | yes/no | Fireplace working
Material Ordered | Main Workflow | Main Workflow | N/A | ROUGH IN |  | Roof replaced | yes/no | Roof ordered
Construction | Main Workflow | Main Workflow | N/A | plumbers rough |  | Windows replaced | yes/no | windows ordered
Final Walk through | Main Workflow | Main Workflow | N/A | Electricians rough |  | Cabinets replaced | yes/no | cabinets ordered
Staging | Main Workflow | Main Workflow | N/A | hvac rough |  | Appliances Ordered
Cleaned | Main Workflow | Main Workflow | N/A |  |  | Countertops ordered
Pictures | Main Workflow | Main Workflow | N/A | Prep stage |  | Pool | yes/no | Pool started
Offer Accepted | Main Workflow | Main Workflow | N/A | Durarock bathrooms |  | Foundation work | yes/no | Crack guys scheduled
Repair Addendum Sent | Main Workflow | Main Workflow | N/A | Water proof bathrooms |  | Gutters Ordered
Repaired Addendum Finished | Main Workflow | Main Workflow | N/A | Prep interior for paint
Closed on property | Main Workflow | Main Workflow | N/A | Replace/repair baseboard trim etc
Got lockbox back | Main Workflow | Main Workflow | N/A | repair subflooring
All items removed | Construction Workflow | Demo Stage | N/A | repair bad wood exterior
all flooring out | Construction Workflow | Demo Stage | N/A | repair siding
bathrooms demo | Construction Workflow | Demo Stage | N/A | prep exterior for paint
Cabinets out | Construction Workflow | Demo Stage | N/A | Grading away from house
Walls taken out? | Construction Workflow | Demo Stage | Yes/No
ROUGH IN | Construction Workflow | Demo Stage | N/A | Finishing Stage
plumbers rough | Construction Workflow | Demo Stage | N/A | interior painted
Electricians rough | Construction Workflow | Demo Stage | N/A | exterior painted
hvac rough | Construction Workflow | Demo Stage | N/A | bathrooms tiled
Durarock bathrooms | Construction Workflow | Prep stage | N/A | flooring installed
Water proof bathrooms | Construction Workflow | Prep stage | N/A | cabinets installed
Prep interior for paint | Construction Workflow | Prep stage | N/A | countertops installed
Replace/repair baseboard trim etc | Construction Workflow | Prep stage | N/A | backsplash installed
repair subflooring | Construction Workflow | Prep stage | N/A | hardware on cabinets
repair bad wood exterior | Construction Workflow | Prep stage | N/A | light fixtures installed
repair siding | Construction Workflow | Prep stage | N/A | plumbing fixtures installed
prep exterior for paint | Construction Workflow | Prep stage | N/A | door hardware installed
Grading away from house | Construction Workflow | Prep stage | N/A | Gutters Installed
interior painted | Construction Workflow | Finishing Stage | N/A | Appliances installed
exterior painted | Construction Workflow | Finishing Stage | N/A
bathrooms tiled | Construction Workflow | Finishing Stage | N/A | WalkThrough
flooring installed | Construction Workflow | Finishing Stage | N/A | Appliances working
cabinets installed | Construction Workflow | Finishing Stage | N/A | Plumbing fixtures all work
countertops installed | Construction Workflow | Finishing Stage | N/A | All lights and fixtures work
backsplash installed | Construction Workflow | Finishing Stage | N/A | all windows open
hardware on cabinets | Construction Workflow | Finishing Stage | N/A | water heater is on
light fixtures installed | Construction Workflow | Finishing Stage | N/A | HVAC working
plumbing fixtures installed | Construction Workflow | Finishing Stage | N/A | No paint on windows
door hardware installed | Construction Workflow | Finishing Stage | N/A | all doors shut and lock
Gutters Installed | Construction Workflow | Finishing Stage | N/A | grass is cut
Appliances installed | Construction Workflow | Finishing Stage | N/A | garage doors open and shut
Appliances working | Construction Workflow | Walk Through Stage | N/A
Plumbing fixtures all work | Construction Workflow | Walk Through Stage | N/A
All lights and fixtures work | Construction Workflow | Walk Through Stage | N/A
all windows open | Construction Workflow | Walk Through Stage | N/A
water heater is on | Construction Workflow | Walk Through Stage | N/A
HVAC working | Construction Workflow | Walk Through Stage | N/A
No paint on windows | Construction Workflow | Walk Through Stage | N/A
all doors shut and lock | Construction Workflow | Walk Through Stage | N/A
grass is cut | Construction Workflow | Walk Through Stage | N/A
garage doors open and shut | Construction Workflow | Walk Through Stage | N/A
Initial order ordered | Check List Workflow | Checklist Workflow | N/A
Tile ordered | Check List Workflow | Checklist Workflow | N/A
Flooring ordered | Check List Workflow | Checklist Workflow | N/A
Paint ordered | Check List Workflow | Checklist Workflow | N/A
Amazon ordered | Check List Workflow | Checklist Workflow | N/A
Fireplace | Check List Workflow | Checklist Workflow | Fireplace working
Roof replaced | Check List Workflow | Checklist Workflow | Roof ordered
Windows replaced | Check List Workflow | Checklist Workflow | windows ordered
Cabinets replaced | Check List Workflow | Checklist Workflow | cabinets ordered
Appliances Ordered | Check List Workflow | Checklist Workflow | N/A
Countertops ordered | Check List Workflow | Checklist Workflow | N/A
Pool | Check List Workflow | Checklist Workflow | Pool started
Foundation work | Check List Workflow | Checklist Workflow | Crack guys scheduled
Gutters Ordered | Check List Workflow | Checklist Workflow | N/A