## Sheet1
Workflow Description | Workflow Type | Sub Workflow Type | Subworkflow Task
Make an offer | Main Workflow | Main Workflow | N/A
Close On property | Main Workflow | Main Workflow | N/A
Put keys in lockbox | Main Workflow | Main Workflow | N/A
Get utilities Turned on | Main Workflow | Main Workflow | N/A
Verify all utilities are on and not locked | Main Workflow | Main Workflow | N/A
Initial Walk through | Main Workflow | Main Workflow | N/A
Contractor walk through | Main Workflow | Main Workflow | N/A
Material Ordered | Main Workflow | Main Workflow | N/A
Construction | Main Workflow | Main Workflow | N/A
Final Walk through | Main Workflow | Main Workflow | N/A
Staging | Main Workflow | Main Workflow | N/A
Cleaned | Main Workflow | Main Workflow | N/A
Pictures | Main Workflow | Main Workflow | N/A
Offer Accepted | Main Workflow | Main Workflow | N/A
Repair Addendum Sent | Main Workflow | Main Workflow | N/A
Repaired Addendum Finished | Main Workflow | Main Workflow | N/A
Closed on property | Main Workflow | Main Workflow | N/A
Got lockbox back | Main Workflow | Main Workflow | N/A
All items removed | Construction Workflow | Demo Stage | N/A
all flooring out | Construction Workflow | Demo Stage | N/A
bathrooms demo | Construction Workflow | Demo Stage | N/A
Cabinets out | Construction Workflow | Demo Stage | N/A
Walls taken out? | Construction Workflow | Demo Stage | Yes/No
ROUGH IN | Construction Workflow | Demo Stage | N/A
plumbers rough | Construction Workflow | Demo Stage | N/A
Electricians rough | Construction Workflow | Demo Stage | N/A
hvac rough | Construction Workflow | Demo Stage | N/A
Durarock bathrooms | Construction Workflow | Prep stage | N/A
Water proof bathrooms | Construction Workflow | Prep stage | N/A
Prep interior for paint | Construction Workflow | Prep stage | N/A
Replace/repair baseboard trim etc | Construction Workflow | Prep stage | N/A
repair subflooring | Construction Workflow | Prep stage | N/A
repair bad wood exterior | Construction Workflow | Prep stage | N/A
repair siding | Construction Workflow | Prep stage | N/A
prep exterior for paint | Construction Workflow | Prep stage | N/A
Grading away from house | Construction Workflow | Prep stage | N/A
interior painted | Construction Workflow | Finishing Stage | N/A
exterior painted | Construction Workflow | Finishing Stage | N/A
bathrooms tiled | Construction Workflow | Finishing Stage | N/A
flooring installed | Construction Workflow | Finishing Stage | N/A
cabinets installed | Construction Workflow | Finishing Stage | N/A
countertops installed | Construction Workflow | Finishing Stage | N/A
backsplash installed | Construction Workflow | Finishing Stage | N/A
hardware on cabinets | Construction Workflow | Finishing Stage | N/A
light fixtures installed | Construction Workflow | Finishing Stage | N/A
plumbing fixtures installed | Construction Workflow | Finishing Stage | N/A
door hardware installed | Construction Workflow | Finishing Stage | N/A
Gutters Installed | Construction Workflow | Finishing Stage | N/A
Appliances installed | Construction Workflow | Finishing Stage | N/A
Appliances working | Construction Workflow | Walk Through Stage | N/A
Plumbing fixtures all work | Construction Workflow | Walk Through Stage | N/A
All lights and fixtures work | Construction Workflow | Walk Through Stage | N/A
all windows open | Construction Workflow | Walk Through Stage | N/A
water heater is on | Construction Workflow | Walk Through Stage | N/A
HVAC working | Construction Workflow | Walk Through Stage | N/A
No paint on windows | Construction Workflow | Walk Through Stage | N/A
all doors shut and lock | Construction Workflow | Walk Through Stage | N/A
grass is cut | Construction Workflow | Walk Through Stage | N/A
garage doors open and shut | Construction Workflow | Walk Through Stage | N/A
Initial order ordered | Check List Workflow | Checklist Workflow | N/A
Tile ordered | Check List Workflow | Checklist Workflow | N/A
Flooring ordered | Check List Workflow | Checklist Workflow | N/A
Paint ordered | Check List Workflow | Checklist Workflow | N/A
Amazon ordered | Check List Workflow | Checklist Workflow | N/A
Fireplace | Check List Workflow | Checklist Workflow | Fireplace working
Roof replaced | Check List Workflow | Checklist Workflow | Roof ordered
Windows replaced | Check List Workflow | Checklist Workflow | windows ordered
Cabinets replaced | Check List Workflow | Checklist Workflow | cabinets ordered
Appliances Ordered | Check List Workflow | Checklist Workflow | N/A
Countertops ordered | Check List Workflow | Checklist Workflow | N/A
Pool | Check List Workflow | Checklist Workflow | Pool started
Foundation work | Check List Workflow | Checklist Workflow | Crack guys scheduled
Gutters Ordered | Check List Workflow | Checklist Workflow | N/A